## Gantt Chart - Manual Duration
Wing Yan Sang Iman Singh Lim Chung Meng
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 43036 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Exploratory Data Analysis (EDA) | 2017-10-28 | 2017-10-31 | 3 | 0.15 | 2.85 | 5%
Exploratory Data Visualization | 2017-10-28 | 2017-11-01 | 4 | 0 | 4 | 0%
Exploratory Numerical Analysis | 2017-10-28 | 2017-11-01 | 4 | 0 | 4 | 0%
Supervised Methodology | 2017-11-01 | 2017-11-07 | 6 | 0 | 6 | 0%
Unsupervised Methodology | 2017-11-04 | 2017-11-10 | 6 | 0 | 6 | 0%
Further Optimization of Models | 2017-11-07 | 2017-11-12 | 5 | 0 | 5 | 0%
Dummy | 2017-10-28 | 2017-10-28 | 0 | 0 | 0 | 0%
Dummy | 2017-10-28 | 2017-10-28 | 0 | 0 | 0 | 0%
Dummy | 2017-10-28 | 2017-10-28 | 0 | 0 | 0 | 0%
Dummy | 2017-10-28 | 2017-10-28 | 0 | 0 | 0 | 0%
Dummy | 2017-10-28 | 2017-10-28 | 0 | 0 | 0 | 0%
Dummy | 2017-10-28 | 2017-10-28 | 0 | 0 | 0 | 0%
Dummy | 2017-10-28 | 2017-10-28 | 0 | 0 | 0 | 0%
Dummy | 2017-10-28 | 2017-10-28 | 0 | 0 | 0 | 0%
Dummy | 2017-10-28 | 2017-10-28 | 0 | 0 | 0 | 0%
Dummy | 2017-10-28 | 2017-10-28 | 0 | 0 | 0 | 0%
[7 empty] | Key: | Calculated Cell |  | Manual Entry Cell
[8 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.
TASKS
Exploratory Data Analysis (EDA) | Initial Grasp on the Data, Data Cleaning/Preparation, Numerical Analysis